Project Plan: Co-BALT Initiative - Enhancing Organizational Effectiveness

1. Project Name: Co-BALT (Collaboration on Best Alternatives Learning and Technology)

2. Project Goal: Drive continuous improvement and enhance organizational effectiveness by implementing Bottleneck Resolution Method (BRM) based solutions identified through the Co-BALT initiative.

3. Project Objectives:

- Objective 1: Establish Co-BALT team and define operating procedures within [1 month].

- Objective 2: Conduct thorough organizational analysis to identify and prioritize process bottlenecks that hinder key areas within [3 months]. Key areas identified may include, but not limited to:

  - Portfolio Management Structure

  - Balance of Regional Autonomy & HQ Guidance

  - Employee Engagement & Workplace Environment

  - Psychological Safety & Open Feedback Mechanisms

  - Civilian Workforce Support Structure

  - Generational Divide

  - Leadership & Supervisor Training & Development

  - Employee Recognition & Awards Program

  - Process & System Auditing & Assessment

  - Knowledge Sharing & Best Practices (Trip Reports, etc.)

  - Meeting Effectiveness & Action Item Tracking

  - Forum Facilitation & Inclusive Communication

- Objective 3: Implement the principles of BRM to address prioritized bottlenecks, focusing on solutions that leverage technology, learning efforts, and process streamlining, within [6 months per solution area].

- Objective 4: Establish a system for continuous process improvement, monitoring, and feedback collection within the Co-BALT framework.

4. Project Scope:

- In Scope:

  - Formation and operation of the Co-BALT team.

  - Comprehensive organizational analysis and bottleneck identification.

  - Development and implementation of solutions aligned with BRM principles.

  - Utilization of technology, learning initiatives, and process improvements.

  - Continuous monitoring, evaluation, and adaptation of solutions.

  - Establishment of a learning organization.

- Out of Scope:

  - Addressing individual employee performance issues.

  - Implementing major structural changes outside the scope of process improvement.

5. Project Deliverables:

- Co-BALT Charter and Operating Procedures.

- Organizational analysis report detailing identified bottlenecks and recommended prioritization.

- Solution proposals for each prioritized bottleneck, including implementation plans, resource allocation, and anticipated impact.

- Process improvement documentation, training materials, and communication plans for implemented solutions.

- Regular progress reports and feedback mechanisms integrated into Co-BALT meetings.

6. Project Schedule:

- Phase 1: Co-BALT Formation & Analysis [April 7, 2025] - [August 4, 2025]

  - Establish the Co-BALT Team

  - Define Operating Procedures

  - Conduct Organizational Analysis

  - Prioritize Bottlenecks

- Phase 2: Solution Development & Implementation (Ongoing)

  - [Bottleneck Area - TBD] - Develop & Implement Solution [Start Date] - [End Date]

  - [Bottleneck Area - TBD] - Develop & Implement Solution [Start Date] - [End Date]

  - […continue for each prioritized area]

- Phase 3: Continuous Improvement & Monitoring (Ongoing)

  - Monitor solution effectiveness, gather feedback, and adjust.

  - Identify new bottlenecks and areas for improvement through ongoing analysis.

  - Regularly report progress to the Executive Director.

7. Project Resources:

- Human Resources:

  - Executive Sponsor: [Executive Director]

  - Co-BALT Team Lead: [TBD]

  - Co-BALT Members: [Representatives from key departments and functions, subject matter experts, employees with a passion for improvement … TBD]

- Financial Resources: [Estimated Budget per Phase - TBD]

  - Utilize internal manpower ($.../manpower resourcing)

  - Travel cost ($...)

  - Training ($.../internal)

- Technology Resources: [Software/Tools to support collaboration, project management, data analysis, etc.]

  - Utilize approved internal software/tools if available.

  - Identified new software/tools for approval and implementation.

8. Project Risks & Mitigation Strategies:

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Resistance to change | Medium | High | Clear communication, executive buy-in, stakeholder engagement, highlight employee benefits, address concerns proactively. |
| Lack of BRM expertise within Co-BALT | Medium | High | Leverage a BRM consultant or provide in-house training on BRM principles to all Co-BALT members. |
| Insufficient resource allocation | Medium | High | Secure executive buy-in, clearly define resource needs for each phase, and prioritize solutions strategically. |

9. Communication Plan:

- Regular Co-BALT meetings with documented minutes and action items.

- Project updates through email, intranet, or other relevant channels.

- All-hands “town hall” type meetings or presentations to communicate Co-BALT initiatives and successes.

- Feedback mechanisms (surveys, suggestion boxes, etc.) to gather input from all employees.

10. Project Success Criteria:

- Measurable improvements in key performance indicators related to the identified bottlenecks.

- Increased employee engagement and satisfaction.

- Enhanced organizational efficiency, effectiveness, and quality of services.

- A sustainable continuous improvement culture fostered through the Co-BALT efforts.

11. Next Steps:

- Secure final approval for the Co-BALT Charter and Project Plan from the Executive Director.

- Form the Co-BALT team and conduct a kick-off meeting.

- Begin the organizational analysis and bottleneck prioritization.

NOTE: This draft project plan integrates the specific challenges and opportunities outlined in the proposed Co-BALT initiative while adhering to the principles of BRM. By focusing an effort on continuous improvement and collaboration, Co-BALT can drive positive and lasting change within the organization.​